| Supplier (name, role, sign, date) |  | F4E approval (name, role, sign, date) | IO/other acceptance (name, role, sign, date) |
| --- | --- | --- | --- |
| Author | Approver |  |  |

Executive summary for the reporting period

- The project manager’s assessment of the current situation in relation to the forecasts and risks - IPR, CE Marking and dual use technologies - Risk Register - Action List(s) & Status for Management, Technical, Quality and Safety Nuclear and Health, Safety and Environment domain - If needed, Recovery Plan: re-programmed activities required to recover time on any activities behind the program

Contract status (recommended format follows)

- Tasks* achieved during the period - Tasks not achieved during the period - Tasks foreseen for the next period - Postponed planned tasks *Control Points from MCP/MIP, Planned Milestones/Meetings/Reviews, Unforeseen Tasks (e.g. Actions from NCRs/Deviations/Audits)

| Activity ID/ Title | Initial Expected Date | Current Planned Date | Planned last month | Actual Execution date | Closure Reference document | Justification for the Delay |
| --- | --- | --- | --- | --- | --- | --- |

Procurement Status of items impacting schedule

- Material Procurement, Long Lead Items, Dual-use Items

Schedule Management

- Schedule Variance, Entire updated schedule (source file), List of changes affecting schedule, Main milestones 45 degree chart, EVM trend (schedule) from the beginning of the contract and the justification in case of discrepancies.

Financial Status

- Milestone Payment Plan - Forecasted invoices planned to be submitted to F4E (planned amount and date) / 3 months forecast - Cost Management: Cost at a contract signature (date), List of changes affecting cost (date and corresponding increase), Total cost of changes, Total as at the date of the report, Deviations with the cost impact in the approval circuit including proposed cost, EVM trend (cost) from the beginning of the contract and the justification in case of discrepancies.

Technical Status

- Status of the progress of work being performed by the Supplier - Status Documentation submission - A summary of Subcontractors progress reports identifying main issues impacting F4E activities, when applicable

Manufacturing Status

Quality Assurance Status

- Audit & Monitoring plan and status and results at all levels (including internals) - Status list of all NCRs (including INC) and Deviations - Status of the Critical Quality Items/Activities - Qualification status - Status of activities (internal and at Subcontractor) requiring quality representative involvement

Nuclear Safety Status

Software development

- Process and product metrics, Status of verification activities

For Suppliers working on ITER site

- H&SE incidents - HS&E reviews and assessment