## Risk Register
|  |  | RISK REGISTER | [24 empty] | Document Reference No: | [11 empty] | F4E |  |  |  | Less than 10M Euros |  | Lessthan10
[28 empty] | Issue Date: | [11 empty] | Supplier |  |  |  | Between 10M and 50M Euros | . | Between10and50
[28 empty] | Revision Number: | [16 empty] | .
.
F4E / Supply Chain Risk Register: |  |  | Supplier | [41 empty] | .
CONTRACT REF NUMBER: | [44 empty] | .
COST IMPACT SCALE: |  |  | Less than 10M Euros | [25 empty] | Lessthan10 | <10M COST Impact | 10M to 50M COST Impact | 10M to 50M COST Impact
PROJECT TITLE:
PROJECT TEAM:
PROJECT MANAGER:
Risk Description | [10 empty] | Current Impact Assessment |  |  |  |  | Risk Response | [5 empty] | Residual Impact Assesment |  |  |  |  | Technical |  | Comments | Pre Mitigation | [6 empty] | Post Mitigation
Risk ID | Type | Risk Owner | Risk Category | Status | Risk Title | ("As a result of...") | ("There is a risk that...") | ("Resulting in...") | Exposure Start | Expiry Date | Likelihood | Cost Impact (€k) | Schedule (days) | Risk Score | Risk Level | Treatment | Response Actions | Action Owner | Initiation Date for each action | Completion Date for each action | Status | Likelihood | Cost Impact (€k) | Schedule (days) | Risk Score | Risk Level | Flag | Description | Notes and Justification | Probability Rank | Cost Impact | Time Impact | Threat Score | Threat Level | Opp Score | Opp Level | Probability Rank | Cost Impact | Time Impact | Score | Threat Level | Opp Score | Opp Level
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | Likelihood | Score | Less than 10M COST Impact | Between 10M and 50M COST Impact | Score | SCHEDULE Impact | Score | Symbol | Impact Discription
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | Very Low <=10% | 1 | Very Low <=50k€ | Very Low <=0.5M€ | 1 | Very Low <=1week | 1 | – | Minimal or no consequence to technical performance
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | Low 10% to 30% | 2 | Low >50k€ <=500k€ | Low >0.5M€ <=1M€ | 4 | Low >1week <=3month | 4 | ★ | Minor reduction in technical performance or supportability, can be tolerated with little or no impact on program
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | Medium 30% to 50% | 3 | Medium >500k€ <=1M€ | Medium >1M€ <=2M€ | 9 | Medium >3Month <=6Months | 9 | ☑ | Moderate reduction in technical performance or supportability with limited impact on program objectives
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | High 50% to 80% | 4 | High >1M€ <=2M€ | High >2M€ <=5M€ | 16 | High >6Months <=1year | 16 | ❢ | Significant degradation in technical performance or major shortfall in supportability; may jeopardize program success
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low | Very High >80% | 5 | Very High >2M€ | Very High >5M€ | 25 | Very High >1year | 25 | ⓧ | Severe degradation in technical performance; Cannot meet baseline or key technical/ supportability threshold; will jeopardize program success
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low
[14 empty] | 0 | 0 | [9 empty] | 0 | 0 |  | 0 |  | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | LOW | FALSE | FALSE | FALSE | 0 | 3. LOW | 0 | Low

## THREAT Rating Information
THREAT RATING
LIKELIHOOD of risk occurrence
Value |  | Description
Very Low | 1 | Probability of occurrence < 10%. | A risk is an event that "may" occur. The probability of it occurring can range anywhere from just above 0 percent to just below 100 percent. (Note: It can't be exactly 100 percent, because then it would be a certainty, not a risk. And it can't be exactly 0 percent, or it wouldn't be a risk
Low | 2 | Probability of occurrence > =10% but <30%
Medium | 3 | Probability of occurrence > = 30% but <50%
High | 4 | Probability of occurrence >= 50% but <80%
Very High | 5 | Probability of occurrence > = 80%
TECHNICAL IMPACT
Value |  | Technical Performance Impact
Very Low | – | Minimal or no consequence to technical performance
Low | ★ | Minor reduction in technical performance or supportability, can be tolerated with little or no impact on program
Medium | ☑ | Moderate reduction in technical performance or supportability with limited impact on program objectives
High | ❢ | Significant degradation in technical performance or major shortfall in supportability; may jeopardize program success
Very High | ⓧ | Severe degradation in technical performance; Cannot meet baseline or key technical/ supportability threshold; will jeopardize program success
COST IMPACT
Value |  | <10M COST Impact | 10M to 50M COST Impact
Very Low | 1 | Very Low <=50k€ | Very Low <=0.5M€
Low | 2 | Low >50k€ <=500k€ | Low >0.5M€ <=1M€
Medium | 3 | Medium >500k€ <=1M€ | Medium >1M€ <=2M€
High | 4 | High >1M€ <=2M€ | High >2M€ <=5M€
Very High | 5 | Very High >2M€ | Very High >5M€
SCHEDULE IMPACT
Value |  | DELAY on Milestone (at project level Integrated Project Schedule Milestones)
Very Low | 1 | No delays on milestones (< 1 Week)
Low | 2 | 1 Week ≤ DELAY < 3 month
Medium | 3 | 3 month ≤ DELAY < 6 months
High | 4 | 6 month ≤ DELAY < 1 year
Very High | 5 | DELAY ≥ 1 year
RISK
Level |  | Actions
3. LOW |  | They are included in the risk file and reviewed by WPM concerned. Actions are evaluated in order to reduce the risk.
2. MEDIUM |  | Same as level MEDIUM plus definition of specific mitigation actions. These actions are defined by the WPM concerned with the risk, who identifies also possible trigger events to start them. The owner monitors the risks and these trigger events.
1. HIGH |  | Planned mitigation actions are started as scheduled. The risk owner is designated directly by the PM, who closely monitors the effectiveness of the mitigation actions at each project review meeting
THREATS HANDLING STRATEGIES
Avoidance | This strategy focuses on totally eliminating the specific threat or risk-driving event usually by eliminating the potential that the risk event can occur (i.e. – take action to drive the likelihood of occurrence to zero). This can be accomplished through total structure, system, or component redesign, or by selecting an alternate design approach, which does not include the particular risk event, etc. Generally it is not possible to eliminate all risks, but specific risk events can often be eliminated with this strategy.
Reducing | This strategy identifies specific steps or actions that will improve the chances that an activity will succeed by: • Reducing the likelihood of the occurrence of the risk event, or • Mitigating the consequence of a risk event, or • A combination of the two.
Transfer | This strategy is used when the scope of work with identified risks can be transferred to another activity or entity, especially when this risk can be more easily handled within the receiving activity or entity. A risk can be transferred to an outside organization however the individual or organization receiving the risk must accept the risk transfer.
Accept | Accepting a risk is essentially a “no action” strategy. Low risks are typically accepted.

## OPPORTUNITY Rating Information
OPPORTUNITY RATING
LIKELIHOOD of opportunity realization
Value |  | Description
Very Low | 1 | Probability of realization < 10%. | A risk is an event that "may" occur. The probability of it occurring can range anywhere from just above 0 percent to just below 100 percent. (Note: It can't be exactly 100 percent, because then it would be a certainty, not a risk. And it can't be exactly 0 percent, or it wouldn't be a risk
Low | 2 | Probability of realization > =10% but <30%
Medium | 3 | Probability of realization > =30% but <50%
High | 4 | Probability of realization > =50% but <80%
Very High | 5 | Probability of realization > 80%
TECHNICAL IMPACT
Value |  | Technical Performance Impact
Very Low | – | Minimal or no consequence to technical performance
Low | ★ | Minor improvement in technical performance or supportability, can be achieved with little or no impact on program
Medium | ☑ | Moderate improvement in technical performance or supportability with limited impact on program objectives
High | ❢ | Major improvement in technical performance or supportability; will improve program success
Very High | ⓧ | Significant improvement in technical performance; Meets baseline or key technical/ supportability threshold; will significantly improve program success
COST IMPACT
Value |  | <10M COST Impact | 10M to 50M COST Impact
Very Low | 1 | Negligible <=50k€ | Negligible <=0.5M€
Low | 2 | Low >50k€ <=500k€ | Low >0.5M€ <=1M€
Medium | 3 | Medium >500k€ <=1M€ | Medium >1M€ <=2M€
High | 4 | High >1M€ <=2M€ | High >2M€ <=5M€
Very High | 5 | Very High >2M€ | Very High >5M€
SCHEDULE IMPACT
Value |  | IMPROVEMENT on Milestone (Contract Milestones)
Very Low | 1 | No improvements on milestones (< 1 week)
Low | 2 | 1 week ≤ IMPROVEMENT < 3 month
Medium | 3 | 3 month ≤ IMPROVEMENT < 6 months
High | 4 | 6 month ≤ IMPROVEMENT < 1 year
Very High | 5 | IMPROVEMENT ≥ 1 year
OPPORTUNITY
Level |  | Actions
1. LOW |  | They are included in the risk file and reviewed by WPM concerned. Actions are evaluated in order to enhance the oportunity
2. MEDIUM |  | An owner is appointed to monitor the risk evolution and report to the WPM concerned. Actions are evaluated in order to enhance the oportunity
3. HIGH |  | Planned handling actions are started as scheduled. The risk owner is designated directly by the PM, who closely monitors the effectiveness of the actions at each project review meeting
OPPORTUNITY HANDLING STRATEGIES
Enhance | This strategy modifies the “size” of an opportunity by increasing probability and/or positive impact Events. Seeking to facilitate or strengthen the cause of the opportunity, and proactively targeting and reinforcing its trigger conditions, might increase probability. Impact drivers can also be targeted, seeking to increase the project’s susceptibility to the opportunity.
Exploit | This strategy may be selected for Events with positive impacts where the organization wishes to ensure that the opportunity is realized. This strategy seeks to eliminate the uncertainty associated with a particular upside Event by making the opportunity definitely happen. Directly exploiting responses includes assigning more talented resources to the project to reduce the time to completion or to provide better quality than originally planned.
Facilitate | Sharing a positive Event involves allocating ownership to a third party who is best able to capture the opportunity for the benefit of the project. Examples of sharing actions include forming risk-sharing partnerships, teams, special-purpose companies, or joint ventures, which can be established with the express purpose of managing opportunities
Reject | This is to document that the opportunity was considered, but not implemented. Reasons for not implementing an opportunity may be due excessive implementation cost and/or schedule increase, compared to the return from this element.

## Risk Category
Risk Categories
1. Requirement/Scope Definition
| 1.1 | Requirements | 1.1 Requirements
|  | Are the functions or Requirements undefined, incomplete or unclear? If so what is the concern? | 1.2 Scope Definition
|  | Insufficient Requirements analysis performed? If so why is this a concern? | 2.1 Design Complexity
|  | Are there any unstable Requirements? If so what is the concern? | 2.2 Design Maturity
|  | Are the Requirements difficult to trace? If so what is the concern? | 2.3 Design Development
|  | Is there actual or potential non-compliant or invalidated Requirements? | 2.4 Design Integration
| 1.2 | Scope Definition | 3.1 Stakeholder
|  | Is the Scope clearly defined and understood | 3.2 Regulatory
|  | Are the parties clear on what they are delivering/providing | 3.3 Environmental
|  | Are there any gaps between Requirement and Scope | 4.1 Safety
|  | Is the Requirement for the System/Sub System clear | 4.2 Security
|  | Is there any ambiguity in understanding between parties | 4.3 Quality
5.1 Supply Chain
2. Design |  |  | 5.2 Contractor Capability
| 2.1 | Design Complexity | 6.1 Technology
|  | Are there any complex design features that present a particular cause for concern? | 6.2 Information Technology
|  | Is the Design compromised by a need to complete for the PA or other milestone? | 7.1 Fabrication/Manufacture
|  | Is there potential for incompatibility between designs? | 8.1 Construction Strategy
|  | Are there numerous or unclear bases of assumptions? | 8.2 Construction
9.1 Interfaces
| 2.2 | Design Maturity | 9.2 Integration
|  | Are aspects of the Design unresolved due to unclear requirements and scope? | 9.3 Assembly
|  | Inadequate or conflicting design documentation? | 10.1 Testing
|  | Are there any known or potential errors or omissions in the Design? | 10.2 Operations
11.1 Free Category - enter here any other risk that does not comfortably fit into the above
| 2.3 | Design Development
Is the design still being developed…particularly relevant as it nears PA signature?
Is there potential for the design to advance and not be effectively communicated?
Is the change process capturing Design changes and are these and effectively communicated?
| 2.4 | Design Integration
Is the design effectively communicated? If No what are the concerns…?
Are there any known or potential unstable or not frozen interfaces?
Are there any known or potential design integration issues?
3. Stakeholder/Regulatory/Environmental
| 3.1 | Stakeholder
What are the key Stakeholders concerns? Do these present a cause for concern?
Are there any particular Stakeholders concerns that are currently causing problems?
Are there any likely Stakeholder concerns that will cause problems in the future?
| 3.2 | Regulatory
Are there any particular French Regulation concerns that are currently causing problems?
Are there any likely French Regulator concerns that will cause problems in the future?
| 3.3 | Environmental
Is an Archaeological Review required? What are the concerns?
Is an Environmental assessment required? What are the concerns?
Any Environmental Permits or licenses required? What are the concerns?
Are there any known or potential Environmental concerns?
Potential for releases or additional releases?
Undefined disposal methods?
4. Safety/Security/Quality
| 4.1 | Safety
Does the system or subsystem have:
· Hazardous material involved?
· Significant contamination potential?
· New design basis accidents or other unreviewed safety questions?
· Safety class or safety significant systems (or other non-nuclear equivalent) involved?
Is the French Regulators approval or safety basis documentation requirements a cause for concern. Is it likely to take longer than planned?
| 4.2 | Security
Are there any security related issues with any aspect of the system that are currently/or are envisaged that will cause problems?
| 4.3 | Quality
Is precision work required and if so are there any perceived difficulties?
Does the contractor community have the required skill?
Are QA standards well-defined?
Are QA processes understood?
Change without careful analysis and integration into the design?
Lack of information transfer in-between design, manufacturing, and assembly teams?
Lack of (or limited) tests for budget or schedule reasons?
Out of tolerance deviations from / during manufacturing?
Is rework expected due to nature of project tolerances?
5. Supply Chain/Contractor Capability
| 5.1 | Supply Chain
Is there sufficient depth in the supply chain to ensure competition?
Is there potential for unavailability of qualified vendors or contractors?
Does the supply chain have sufficient spare capacity to undertake the work?
Is the supply chain sufficiently qualified, experienced and possesses the necessary skills to perform and deliver the work?
Does thecontractor have the requisite experience, skills to ensure the supply chain delivers?
| 5.2 | Contractor Capability
Is there potential for the unavailability of facilities?
Does the contractor community have the required skill?
Are there any uncertainties associated with the contractor process?
Are there any uncertainties associated with the contractor stability?
Are there any known or potential difficulties with the availabliity of materials or parts?
6. Technology/Information Technology
| 6.1 | Technology
Does R&D support the technology development? If not what is the main concern?
Is there any unknown or unclear technology in any part of the system that is a cause for concern?
Is there a requirement for a new application of an existing technology that is or will present a problem?
Is there modernized /advanced technology in an existing application?
Is there potential for technology under development that will not perform as expected (specific items)?
Is there a requirement for new technology that is presenting a cause for concern?
Is there potential for new technologies not to be properly developed by the R&D programme
Is there potential that integration of the technology into the ITER system fails?
Is there potential that technology no longer supported?
Is Industry in place?
| 6.2 | Information Technology
Are there any known or potential problems associated with IT or Software?
Is there potential for incompatibility (Hardware/Software) across systems?
7. Fabrication/Manufacture
| 7.1 | Fabrication/Manufacture
Are there any problems/potential problems associated with the fabrication capabilities within the supply chain?
Are design documents inadequate to develop manufacturing plans or control specifications?
Is the system for manufacturing management inadequate to control the quality, cost, and schedule?
Manufacturing plans are late or insufficient to manage the fabrication of components
Manufacturing processes cannot produce components that meet the design criteria
The system for disposition of non-conformances is inadequate to meet the schedule
The systems engineering function is inadequate to integrate the component/system tolerances and specifications
Is there a risk to fabrication and assembly from the effects of cumulative tolerances
Is there potential for machinery failure in fabrication phase?
Demands on the QA/QC system will delay the manufacturing schedule
8. Construction Strategy/Construction
| 8.1 | Construction Strategy
Are there any known difficulties with the construction strategy?
| 8.2 | Construction
Site ground conditions are not as expected?
Is the Building design not adequately integrated with systems to be installed?
Is there a risk of equipment & component degradation during shipping and storage?
Is there a risk of availability of lay down space?
Are there any conflicts between buildings and plant installation?
Is thereany maintenance issues to equipment & components in storage?
Are there conflicts between Subcontractor working areas?
Is there potential for site safety systems and management will be ineffective in ensuring worker safety?
9. Interface/Integration/Assembly
| 9.1 | Interfaces
Are there any unstable or not frozen interfaces?
Are multiple project interfaces involved and do these present a concern?
Are all interfaces for this system understood and documented?
Is there potential for insufficient systems integration?
Do other adjacent Systems understand clearly this System requirements?
| 9.2 | Integration
Are there any known or potential integration issues?
Is the integration of buildings and systems clear?
Is the integration of system to system understood?
Is the integration of system to building understood?
| 9.3 | Assembly
Is the Assembly schedule inadequately defined?
Is the Assembly multi shift working pattern unachievable?
Is the Assembly unable proceed due to unavailability of Buildings?
Is the Assembly unable to proceed due to the unavailability of Plant & Equipment?
Is there potential for difficulties to arise during Assembly phase
Is there potential for re-work to occur during Assembly phase due to for example incompatibilities of components or systems?
Is there a risk of Assembled plant tolerances being exceeded?
Is there is a risk of Assembly unable to proceed due to incompatibility issues i.e. the affects of compounded tolerances?
10. Testing/Operations
| 10.1 | Testing
Are there any problems foreseen in the Testing phase?
| 10.2 | Operations
Are there any problems foreseen in the Operations phase?
Is there potential for major component/equipment failure in Operations phase (list specific systems)?
Difficulties envisaged due to multiple subcontractors will have unplanned conflicts working in the same area?
Difficulties envisaged from multi-shift commissioning work that will not be achievable?
Is planning immaturity within Operations a potential problem?
Is there a potential problem due to maintenance routines not being adequately defined?
Insufficient spare parts will be available?
11. Other
| 11.1 | Free Category - enter here any other risk that does not comfortably fit into the above